## Project Schedule
<Project Name>
Date:
Project Manager:
Project Schedule
Task Name | Duration | Start | Finish | Resource Names | % Complete | Notes
<Project Name>
Initiating
Create Project Charter / Business Case | 1 day | 2012-01-09 | 2012-01-09 | Project Manager | 100% | Insert additional details
Planning
Schedule Kickoff meeting and distribute Kickoff Meeting Agenda | 1 day | 2012-01-16 | 2012-01-16 | Project Manager | 100% | Insert additional details
Hold Project Kickoff Meeting | 0 days | 2012-01-17 | 2012-01-17 |  | 100%
Create Project Schedule | 4 days | 2012-01-17 | 2012-01-20 | Project Manager | 100% | Insert additional details
Create Project Budget | 1 day | 2012-01-19 | 2012-01-19 | Project Manager | 100% | Insert additional details
Create Resource Plan | 1 day | 2012-01-19 | 2012-01-19 | Project Manager | 100% | Insert additional details
Create Communications Plan | 1 day | 2012-01-23 | 2012-01-23 | Project Manager | 100% | Insert additional details
Create Risk Plan | 1 day | 2012-01-23 | 2012-01-23 | Project Manager | 100% | Insert additional details
Schedule weekly status meeting | 1 day | 2012-01-16 | 2012-01-16 | Project Manager | 100% | Insert additional details
Planning Phase Complete | 0 days | 2012-01-27 | 2012-01-27 |  | 0%
Executing / Controlling
Status Meetings
Distribute Meeting Agenda for weekly status meetings | 1 day | 2012-01-27 | 2012-01-27 | Project Manager | 0% | Insert additional details
Hold weekly status meetings and distribute Meeting Notes | 40 days | 2012-01-30 | 2012-03-26 | Project Manager | 0% | Insert additional details
Maintain Project Deliverables
Maintain Project Schedule | 44 days | 2012-01-30 | 2012-03-30 | Project Manager | 0% | Insert additional details
Maintain Project Budget | 44 days | 2012-01-30 | 2012-03-30 | Project Manager | 0% | Insert additional details
Maintain Resource Plan | 44 days | 2012-01-30 | 2012-03-30 | Project Manager | 0% | Insert additional details
Maintain Communications Plan | 44 days | 2012-01-30 | 2012-03-30 | Project Manager | 0% | Insert additional details
Maintain Risk Plan | 44 days | 2012-01-30 | 2012-03-30 | Project Manager | 0% | Insert additional details
Create and maintain Issues / Actions List | 44 days | 2012-01-30 | 2012-03-30 | Project Manager | 0% | Insert additional details
Create and maintain Change Log | 44 days | 2012-01-30 | 2012-03-30 | Project Manager | 0% | Insert additional details
Create Status Report for monthly distribution | 44 days | 2012-01-30 | 2012-03-30 | Project Manager | 0% | Insert additional details
Executing / Controlling Phase Complete | 0 days | 2012-03-30 | 2012-03-30 |  | 0%
Go-Live | 0 days | 2012-04-01 | 2012-04-01 |  | 0%
Closing
Create Project Closeout document | 5 days | 2012-04-02 | 2012-04-06 | Project Manager | 0% | Insert additional details
Hold project closeout meeting | 1 day | 2012-04-09 | 2012-04-09 | Project Manager | 0% | Insert additional details
Note on A8: Provide a brief description of the task. (NOTE: Keep task names clear and concise, and start each task with a verb (e.g. - create, schedule, distribute, etc.).
Note on B8: Enter the estimated time it will take to complete the task.
Note on C8: Enter the date that the task should begin.
Note on D8: Enter the date that the task should end.
Note on E8: Enter the name(s) of the individual(s) responsible for completing the task.
Note on F8: Provide the estimated percent complete for the task.
Note on G8: Enter any additional details or comments related to the task.